## Sheet1
Requirement: |  | WBS | [9 empty] | DATABASE
Fitur | Extension | Division | Work | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | users | beasiswa | beasiswa_content | news | news_content | ukm | ukm_content | event | event_content
Beasiswa | Kategori | Backend | Database Design | [8 empty] | id | id | beasiswa_id | id | news_id | id | ukm_id | id | event_id | bar: 2016-02-29
| Tanggal | Backend | Routing | [8 empty] | username | kategori | id | header_pic | id | name | id | kategori | id | bar: 2016-02-29 to 2016-03-07; 2016-03-28 to 2016-04-18
News |  | Frontend | /home | [8 empty] | password | sumber | type | update date(otomatis) | type | header_pic | type | sumber | type | bar: 2016-02-29 to 2016-03-07
UKM |  | Frontend | /beasiswa | [8 empty] | auth_level | jumlah | content | creation date(otomatis) | content |  | content | header_pic | content | bar: 2016-02-29 to 2016-03-07
Event | Binding ke UKM | Frontend | /news | [8 empty] | update_date(otomatis) | header_pic | [5 empty] | tempat | bar: 2016-02-29 to 2016-03-07
Admin | Organize Staff | Frontend | /ukm | [8 empty] | creation_date(otomatis) | update_date(otomatis) | [5 empty] | event_date | bar: 2016-02-29 to 2016-03-07
Search | Search | Frontend | /event | [8 empty] | status | creation_date(otomatis) | [5 empty] | update date(otomatis) | bar: 2016-02-29 to 2016-03-07
|  | Backend | Home Controller - index | [9 empty] | deadline_date | [5 empty] | creation date(otomatis) | bar: 2016-02-29 to 2016-03-07
Sitemap: |  | Backend | Beasiswa Controller - index | bar: 2016-02-29 to 2016-03-07
Fitur | Extension | Backend | News Controller - index | bar: 2016-02-29 to 2016-03-07
/home |  | Backend | UKM Controller - index | bar: 2016-02-29 to 2016-03-07
/beasiswa | /beasiswa/{id} | Backend | Event Controller - index | bar: 2016-02-29 to 2016-03-07
| /beasiswa/new | Frontend | /admin/organize | bar: 2016-03-07
| /beasiswa/edit/{id} | Frontend | /beasiswa/{id} | bar: 2016-03-07
/news | /news/{id} | Frontend | /news/{id} | bar: 2016-03-07
| /news/new | Frontend | /ukm/{id} | bar: 2016-03-07
| /news/edit/{id} | Frontend | /event/{id} | bar: 2016-03-07
/ukm | /ukm/{id} | Backend | Home Controller - detail | bar: 2016-03-07; 2016-03-28
| /ukm/new | Backend | Beasiswa Controller - detail | bar: 2016-03-07; 2016-03-28
| /ukm/edit/{id} | Backend | News Controller - detail | bar: 2016-03-07; 2016-03-28
/event | /event/{id} | Backend | UKM Controller - detail | bar: 2016-03-07; 2016-03-28
| /event/new | Backend | Event Controller - detail | bar: 2016-03-07; 2016-03-28
| /event/edit/{id} | Frontend | /search?query={} | bar: 2016-03-28
/admin | /admin/organize | Frontend | /beasiswa/new | bar: 2016-03-28
/search | /search?query={} | Frontend | /news/new | bar: 2016-03-28
|  | Frontend | /ukm/new | bar: 2016-03-28
|  | Frontend | /event/new | bar: 2016-03-28
|  | Backend | Home Controller - new | bar: 2016-03-28 to 2016-04-04
|  | Backend | Beasiswa Controller - new | bar: 2016-03-28 to 2016-04-04
|  | Backend | News Controller - new | bar: 2016-03-28 to 2016-04-04
|  | Backend | UKM Controller - new | bar: 2016-03-28 to 2016-04-04
|  | Backend | Event Controller - new | bar: 2016-03-28 to 2016-04-04
|  | Frontend | CSS/AJAX/Animation/Theme | bar: 2016-03-28 to 2016-04-04
|  | Frontend | /beasiswa/{id}/edit | bar: 2016-03-28 to 2016-04-04
|  | Frontend | /news/{id}/edit | bar: 2016-03-28 to 2016-04-04
|  | Frontend | /ukm/{id}/edit | bar: 2016-03-28 to 2016-04-04
|  | Frontend | /event/{id}/edit | bar: 2016-03-28 to 2016-04-04
|  | Backend | Home Controller - edit | bar: 2016-03-28 to 2016-04-11
|  | Backend | Beasiswa Controller - edit | bar: 2016-03-28 to 2016-04-11
|  | Backend | edits Controller - edit | bar: 2016-03-28 to 2016-04-11
|  | Backend | UKM Controller - edit | bar: 2016-03-28 to 2016-04-11
|  | Backend | Event Controller - edit | bar: 2016-03-28 to 2016-04-11